## Product-Backlog
PRODUCT BACKLOG MULTI-LEVEL APPROVAL WORKFLOW ENGINE
PRODUCT BACKLOG REPORT
ID | AS A … | I WANT TO … | SO THAT … | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
101 | As a User | I want to login securely | so that I can access my personalized dashboard. | High | 1 | Not Started | Not Started | High
102 | As a User | I want to login securely. | so that I can access my dashboard securely. | Medium | 1 | Not Started | In Progress | Medium
103 | As an admin. | I want to define approval levels | so that I can set the hierarchy (e.g. Mgr -> HR). | High | 1 | Not Started
104 | As an admin. | I want to edit existing workflows | so that I can update the hierarchy when roles change. | High | 2 | Not Started
105 | As an admin. | I want to manage user roles (Admin, Manager, User) | so that to control system access. | Medium | 7 | Not Started
106 | As a Requester | I want to submit a new request form | so that it can be reviewed. | High | 3 | Not Started
107 | As a Requester | I want to track my request status | so that I can see its real-time progress. | Medium | 6 | Not Started
108 | As a Requester | I want to upload PDF/Images with my request | so that approvers have more context. | Low | 3 | Not Started
109 | As an Approver | I want to Approve or Reject a request | so that the workflow moves forward. | High | 4 | Not Started
110 | As an Approver | I want to add rejection comments | so that the user knows why it was denied. | High | 5 | Not Started
111 | As an Approver | I want to login with my credentials | so that I can access my dashboard securely. | Medium | 5 | Not Started
TOTAL |  |  |  |  | 38

## Sprint-Backlog
AGILE SPRINT BACKLOG MULTI-LEVEL APPROVAL WORKFLOW ENGINE
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | ORIGINAL ESTIMATE | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | SPRINT REVIEW
User Story #101 – User Login & System Setup
Initial Database Schema Design (SQL Server) |  | Aastha Bilochi | In Progress
Setup Web API Project Structure (.NET Core) |  | Aastha Bilochi | In Progress
Setup React/Angular Frontend Boilerplate |  | Aastha Bilochi | In Progress
Configure Identity Server & JWT Setup |  | Aastha Bilochi | In Progress
User Story #102 – Admin Role Management
Create Admin UI for User Role Assignment |  | Aastha Bilochi | In Progress
Backend API for Role-Based Access Control |  | Aastha Bilochi | In Progress
Middleware to restrict unauthorized access |  | Aastha Bilochi | In Progress
Unit Testing for Identity/Auth modules |  | Aastha Bilochi | Not Started
User Story #103 – Approval Workflow Builder
Create UI to define dynamic Approval Levels |  | Aastha Bilochi | Not Started
API to save and update workflow sequences |  | Aastha Bilochi | Not Started
Logic to handle N-levels of approval routing |  | Aastha Bilochi | Not Started
Validation for workflow level configuration |  | Aastha Bilochi | Not Started
User Story #104 – Request Submission Form
Design Request Form UI with input fields |  | Aastha Bilochi | Not Started
Implement File Upload for supporting docs |  | Aastha Bilochi | Not Started
API to link new requests to Level 1 manager |  | Aastha Bilochi | Not Started
Error handling for mandatory field validation |  | Aastha Bilochi | Not Started
User Story #105 – Approver Action Center
Design Dashboard for pending approval tasks |  | Aastha Bilochi | Not Started
Implement 'Approve' logic (move to next lvl) |  | Aastha Bilochi | Not Started
Implement 'Reject' logic with mandatory comments |  | Aastha Bilochi | Not Started
Real-time update of request status in DB |  | Aastha Bilochi | Not Started
User Story #106 – Live Status Tracking
Build Progress Bar for request status tracking |  | Aastha Bilochi | Not Started
Create Audit Logs for action history |  | Aastha Bilochi | Not Started
UI to view full history of approvals/rejections |  | Aastha Bilochi | Not Started
Search and Filter functionality for past requests |  | Aastha Bilochi | Not Started
User Story #107 – System Notifications & Docs
Integrate SMTP for automated email alerts |  | Aastha Bilochi | Not Started
Bug fixing and Security vulnerability testing |  | Aastha Bilochi | Not Started
Prepare Final README and Deployment guide |  | Aastha Bilochi | Not Started
GitHub Repo Cleanup & Final Submission |  | Aastha Bilochi | Not Started
TOTAL |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0

## User story
S.NO | User Story | Acceptance Criteria
1 | As a user, I want to login securely so that I can access my account.
3 | As a Requester, I want to submit a request form so that it can be processed for approval. | Given all mandatory fields are filled, When I click submit, Then the request status should change to "Level 1 Pending". Given missing data, When I click submit, Then fields should highlight in red.
4 | As an Approver, I want to see a list of pending requests so that I can take action.
5
6 | As a Manager, I want to add comments while rejecting so that the user knows the reason. | Given a rejection action, When I click reject, Then a comment box must appear and be mandatory to fill.
7 | As a System, I want to send an email notification so that users are alerted of updates.
8 | As an Admin, I want to edit existing approval workflows so that I can update the hierarchy when roles change. | Given an existing workflow, When I modify a level or person, Then it should reflect in all new requests immediately.
9 | As a User, I want to upload supporting documents (PDF/Images) so that approvers have more context. | Given the request form, When I attach a file and submit, Then the approver should be able to view/download it from their dashboard.
Given the Admin panel, When I add a new approval stage, Then the workflow should be updated instantly.
Given an invalid role, When added to a level, Then system should show a validation error.
As an Admin, I want to define approval levels so that requests follow the right hierarchy.
2
Given valid credentials When the user logs in Then access is granted.
Given valid credentials, When the user logs in, Then access is granted.
Given invalid credentials, When the user logs in, Then error message is shown.
Given a status change, When an action is taken, Then an automated email should be sent to the next person in the workflow.
Given requests assigned to my level, When I open my dashboard, Then I should see "Approve" and "Reject" buttons.
As a Requester, I want to track my request status so that I know where it is stuck
Given a submitted request, When I view my history, Then it should show exactly which level has approved and who is pending.